## Slide 1
Zowe 22PI1 Planning
Introduction and Agenda
Nick Kocsis

## Slide 2
What is PI Planning
Validation of Direction
Collaboration
Identification of Dependencies and communication
Risk Understanding
  Ideally, we should either mitigate or resolve
Outcome: A 3-month plan

## Slide 3
Agenda – Day 1
Opening Announcement. Highlights of the PI Planning
Updates from the Zowe Leadership Committee (8:05 – 8:35)
Updates from the Technical Steering Committee (8:35 – 8:50)
Squad Visions. About 10-15 mins per squad (9:00 – 10:50)
Q&A (10:50 - 11:00)
Squad Breakouts (11:00 – 5:00)
  Create, revise and map Stories to Sprints
  Identify and communicate unknown dependencies
  Identify risks and mitigation plans
  Define the draft PI Objectives
  Assign business value (optional)

## Slide 4
Agenda – Day 2
Opening Announcement (9:05 - 9:10)
Final readouts by Squads (9:10 – 10:00)
Q&A. This time slot is available for the Community to ask questions (10:00 – 10:15)
Break (10:15 – 10:30)
Confidence Vote. Squad Members, Stakeholders & Users (10:30 – 10:45)
  Everyone votes ! 3+ is a go while 2- is a no-go. If necessary, teams rework their plans until a high confidence level can be reached.
  Survey Monkey Link for vote
    Confidence Vote
    A final vote of confidence for all members of Zowe to start the PI. ANY votes 2 or lower means replanning what is necessary.
    5 - Super confident!
    4 - Very confident
    3 - Reasonably confident, but some risk acknowledged. We'll make the PI successfully, but things could happen.
    2 - Not very confident. The PI might be successful, but we really need to discuss a few thing.
    1 - We're planning to fail

## Slide 5
Planning Retrospective and Moving Forward
Squads leave the PI planning event with
  a pre-populated iteration backlog for the upcoming PI.
  They take their team’s PI objectives, iteration plans, and risks back to their regular work area.
  Risks will be captured to ensure that the people responsible for owning or mitigating a risk have the information and are actively managing the risk

## Slide 6
Zowe 22PI1 Close
Thank-you !